## Consent Management Platform
PROJECT TITLE | Consent Management Platform
PROJECT MANAGER | Sittichok
COMPANY NAME | Asia Plus Securities Co.,Ltd.
DATE | 2020-01-20
[7 empty] | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  |  | 2020-05-01
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | bar: 2020-02-01 WEEK 1 to 2020-02-01 WEEK 4
1 | Requirement Collection
1.1 | Requirement Gathering | Suchin | 2020-02-17 | 2020-02-19 | 3 | 100% | bar: 2020-02-01 WEEK 3
2 | Analysis
2.1 | Requirement Analysis | Suchin | 2020-02-20 | 2020-02-21 | 2 | 100% | bar: 2020-02-01 WEEK 3
2.2 | Database Design & Create | Suchin | 2020-02-22 | 2020-02-24 | 3 | 100% | bar: 2020-02-01 WEEK 4
3 | Development
3.1 | ASCO Template Customer Consent Develop | Suchin | 2020-03-02 | 2020-03-06 | 5 | 100% | bar: 2020-03-01 WEEK 1
3.2 | Consent Management API Initial Project | Suchin | 2020-02-25 | 2020-02-28 | 4 | 100% | bar: 2020-02-01 WEEK 4
3.2.1 | - Model Develop | Suchin | 2020-03-09 | 2020-03-13 | 5 | 100% | bar: 2020-03-01 WEEK 2
3.2.2 | - Query User Consent Detail | Suchin | 2020-03-16 | 2020-03-18 | 3 | 100% | bar: 2020-03-01 WEEK 3
3.2.3 | - Query Consent Form | Suchin | 2020-03-19 | 2020-03-20 | 2 | 100% | bar: 2020-03-01 WEEK 3
3.2.4 | - Add New User Accepted Consent | Suchin | 2020-03-23 | 2020-03-27 | 5 | 100% | bar: 2020-03-01 WEEK 4
3.2.5 | - Edit Consent By User | Suchin | 2020-03-30 | 2020-04-03 | 5 | 100% | bar: 2020-03-01 WEEK 5 to 2020-04-01 WEEK 1
3.3 | Consent Management Web Application Initial Project | Suchin | 2020-03-16 | 2020-03-18 | 3 | 100% | bar: 2020-03-01 WEEK 3
3.3.1 | - Add New Consent Form Page | Suchin | 2020-04-06 | 2020-04-08 | 3 | 0% | bar: 2020-04-01 WEEK 2
3.3.2 | - Query Consent Form | Suchin | 2020-04-09 | 2020-04-10 | 2 | 0% | bar: 2020-04-01 WEEK 2
3.3.3 | - Query User User Accepted Consent | Suchin | 2020-04-13 | 2020-04-14 | 2 | 0% | bar: 2020-04-01 WEEK 3
3.3.4 | - Edit/Delete User Accepted Consent | Suchin | 2020-04-15 | 2020-04-17 | 3 | 0% | bar: 2020-04-01 WEEK 3
4 | Document(API Spec,Data Dictionary) | Suchin | 2020-04-20 | 2020-04-24 | 5 | 0% | bar: 2020-04-01 WEEK 4
5 | Testing
5.1 | QA | Piyathida | 2020-04-20 | 2020-04-24 | 5 | 0% | bar: 2020-04-01 WEEK 4
5.2 | UAT |  | 2020-04-27 | 2020-05-08 | 12 | 0% | bar: 2020-04-01 WEEK 5 to 2020-05-01 WEEK 1
6 | Installation/Deployment
6.1 | Production Deployment | BODev Dept. | 2020-05-09 | 2020-05-09 | 1 | 0% | bar: 2020-05-01 WEEK 2
6.2 | Live |  | 2020-05-11 | 2020-05-11 | 1 | 0%

## Sheet1
PROJECT TITLE | Consent Management Platform
PROJECT MANAGER | Sittichok
COMPANY NAME | Asia Plus Securities Co.,Ltd.
DATE | 2020-01-20
[7 empty] | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  |  | 2020-05-01
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 | WEEK 2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | bar: 2020-02-01 WEEK 1 to 2020-02-01 W4
1 | Requirement Collection
1.1 | Requirement Gathering | Suchin | 2020-02-17 | 2020-02-19 | 3 | 100% | bar: 2020-02-01 W3
2 | Analysis
2.1 | Requirement Analysis | Suchin | 2020-02-20 | 2020-02-21 | 2 | 100% | bar: 2020-02-01 W3
2.2 | Database Design & Create | Suchin | 2020-02-22 | 2020-02-24 | 3 | 100% | bar: 2020-02-01 W4
3 | Development
3.1 | ASCO Template Customer Consent Develop | Suchin | 2020-03-02 | 2020-03-06 | 5 | 100% | bar: 2020-03-01 W1
3.2 | Consent Management API Initial Project | Suchin | 2020-02-25 | 2020-02-28 | 4 | 100% | bar: 2020-02-01 W4
3.2.1 | - Model Develop | Suchin | 2020-03-09 | 2020-03-13 | 5 | 100% | bar: 2020-03-01 W2
3.2.2 | - Query User Consent Detail | Suchin | 2020-03-16 | 2020-03-18 | 3 | 100% | bar: 2020-03-01 W3
3.2.3 | - Query Consent Form | Suchin | 2020-03-19 | 2020-03-20 | 2 | 100% | bar: 2020-03-01 W3
3.2.4 | - Add New User Accepted Consent | Suchin | 2020-03-23 | 2020-03-27 | 5 | 100% | bar: 2020-03-01 W4
3.2.5 | - Edit Consent By User | Suchin | 2020-03-30 | 2020-04-03 | 5 | 100% | bar: 2020-03-01 W5 to 2020-04-01 W1
3.3 | Consent Management Web Application Initial Project | Suchin | 2020-03-16 | 2020-03-18 | 3 | 100% | bar: 2020-03-01 W3
3.3.1 | - Add New Consent Form Page | Suchin | 2020-04-06 | 2020-04-08 | 3 | 0% | bar: 2020-04-01 W2
3.3.2 | - Query Consent Form | Suchin | 2020-04-09 | 2020-04-10 | 2 | 0% | bar: 2020-04-01 W2
3.3.3 | - Query User User Accepted Consent | Suchin | 2020-04-13 | 2020-04-14 | 2 | 0% | bar: 2020-04-01 W3
3.3.4 | - Edit/Delete User Accepted Consent | Suchin | 2020-04-15 | 2020-04-17 | 3 | 0% | bar: 2020-04-01 W3
4 | Document(API Spec,Data Dictionary) | Suchin | 2020-04-20 | 2020-04-24 | 5 | 0% | bar: 2020-04-01 W4
5 | Testing
5.1 | QA | Piyathida | 2020-04-20 | 2020-04-24 | 5 | 0% | bar: 2020-04-01 W4
5.2 | UAT |  | 2020-04-27 | 2020-05-08 | 12 | 0% | bar: 2020-04-01 W5 to 2020-05-01 W1
6 | Installation/Deployment
6.1 | Production Deployment | BODev Dept. | 2020-05-09 | 2020-05-09 | 1 | 0% | bar: 2020-05-01 W2
6.2 | Live |  | 2020-05-11 | 2020-05-11 | 1 | 0%